## Slide 1: CSE 805
System Analysis & Design : Lecture 08
Presented By
Noshin Un Noor
Lecturer
Department of CSE
World University of Bangladesh

## Slide 2: What is Project
A project is well-defined task, which is a collection of several operations done in order to achieve a goal (for example, software development and delivery). A Project can be characterized as:
Every project may has a unique and distinct goal.
Project is not routine activity or day-to-day operations.
Project comes with a start time and end time.
Project ends when its goal is achieved hence it is a temporary phase in the lifetime of an organization.
Project needs adequate resources in terms of time, manpower, finance, material and knowledge-bank

## Slide 3: What is Project Management?
Project management is the use of specific knowledge, skills, tools and techniques to deliver something of value to people
Planning
Allocation of Resources
Defining roles and responsibilities
Ensure risk minimization
On-time delivery/Execution

## Slide 4: Need of software project management
Software project management focuses on developing a product that will have a positive effect on an organization. Without project management, a software development team may begin working on a project without any clear vision or guidance, resulting in more frequent errors and confusion.
Part of software project management involves making everyone involved aware of the purpose of the project and what steps are required to meet the end goal. Learn more about project management for software development and what it entails

## Slide 5: What is Project Cost Management
Project cost management is the process of estimating, budgeting and controlling costs throughout the project life cycle, with the objective of keeping expenditures within the approved budget.
For a project to be considered a success, it’s necessary that
it delivers on the requirements and scope
its execution quality is of a high standard
it’s completed within schedule and
it’s completed within budget.
Hence, project cost management is one of the key pillars of project management and is relevant regardless of the domain, be it manufacturing, retail, technology, construction and so on. It helps to create a financial baseline against which project managers can benchmark the current status of their project costs and realign the direction if needed

## Slide 6: Why is Project Cost Management Important?
By implementing efficient cost management practices, project managers can:
Set clear expectations with stakeholders
Control scope creep by leveraging transparencies established with the customer
Track progress and respond with corrective action at a quick pace
Maintain expected margin, increase ROI, and avoid losing money on the project
Generate data to benchmark for future projects and track long-term cost trends

## Slide 7: The Four Steps in Project Cost Management
1. Project Resource Planning
Resource planning is the process of identifying the resources required to execute a project and take it to completion. Examples of resources are people (such as employees and contractors) and equipment (such as infrastructure, large construction vehicles and other specialized equipment in limited supply).
Resource planning is done at the beginning of a project, before any actual work begins

## Slide 8: The Four Steps in Project Cost Management
2. Project Cost Estimation
It is the process of quantifying the costs associated with all the resources required to execute the project.
To perform cost calculations, we need the following information:
Resource requirements (output from the previous step)
Price of each resource (e.g., staffing cost per hour, vendor hiring costs, server procurement costs, material rates per unit, etc.)
Duration that each resource is required
List of assumptions
Potential risks
Past project costs and industry benchmarks, if any
Insight into the company’s financial health and reporting structures

## Slide 9: The Four Steps in Project Cost Management
3. Cost Budgeting
Cost budgeting can be viewed as part of estimation or as its own separate process. Budgeting is the process of allocating costs to a certain chunk of the project, such as individual tasks or modules, for a specific time period. Budgets include contingency reserves allocated to manage unexpected costs.
For example, let’s say the total costs estimated for a project that runs over three years is $2 million. However, since the budget allocation is a function of time, the project manager decides to consider just the first two quarters for now. They identify the work items to be completed and allocate a budget of, say, $35,000 for this time period, and these work items. The project manager uses the WBS and some of the estimation methods discussed in the previous section to arrive at this number

## Slide 10: The Four Steps in Project Cost Management
4. Cost Control
Cost control is the process of measuring cost variances from the baseline and taking appropriate action, such as increasing the budget allocated or reducing the scope of work, to correct that gap. Cost control is a continuous process done throughout the project lifecycle. The emphasis here is as much on timely and clear reporting as measuring

## Slide 11: The Four Steps in Project Cost Management
Earned value management (EVM) is one of the most popular approaches to measuring cost performance. Let’s take an example.
At the end of a week, you measure the progress of task X and find that it’s 25% complete. Now, how do you assess if you are on track to meet the task budget?
First, a project manager calculates the planned value for this task (at the planning stage). Let’s say, Task X has a budget of $4000 and is expected to be 50% complete by the week.
Planned value (PV) of task X by the week = $4000 * .5 = $2000
Earned value (EV) of task X by the week = $4000 * .25 = $1000
Now, you also determine the actual cost (AC) of the work, which involves other variables such as equipment and material costs (say, $800).
Schedule variance = EV – PV = $1000 – $2000 = -$1000.
Cost variance = EV – AC = $1000 – $800 = $200.
The negative schedule variance indicates that the task is falling behind, but the positive cost variance indicates that it’s under budget.
While dealing with hundreds of tasks in huge projects, cost control can provide the level of transparency that decision makers require to respond quickly to the situation.

## Slide 12: Thank You